## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA team | 2025-11-28 | Raw emails contained HTML tags and noise affecting preprocessing | Sprint 1 | Backend Team | Standards | Improved preprocessing and added regex-based normalization | 2025-11-29 | Closed | Verified successfully
2 | QA team | 2025-11-30 | Missing or null email values causing preprocessing failures | Sprint 1 | Backend Team | Maintainability | Removed null records and validated dataset | 2025-12-01 | Closed | Dataset cleaned
3 | QA team | 2025-12-02 | Inconsistent labels found in annotated email samples | Sprint 1 | Data Team | Standards | Standardized category and urgency labels | 2025-12-03 | Closed | Label consistency achieved
4 | QA team | 2025-12-14 | Baseline model accuracy lower than expected | Sprint 2 | ML Team | Logical | Tuned TF-IDF parameters and retrained model | 2025-12-15 | Closed | Accuracy improved
5 | QA team | 2025-12-15 | Logistic Regression model showing overfitting | Sprint 2 | ML Team | Logical | Adjusted feature scaling and regularization | 2025-12-16 | Closed | Overfitting reduced
6 | QA team | 2025-12-17 | Naive Bayes classifier over-predicting dominant class | Sprint 2 | ML Team | Logical | Applied smoothing and balanced dataset | 2025-12-18 | Closed | Balanced predictions
7 | QA team | 2025-12-19 | Transformer model training consuming high memory | Sprint 2 | ML Team | Maintainability | Reduced batch size and switched to DistilBERT | 2025-12-20 | Closed | Stable training
8 | QA team | 2025-12-29 | ML-only urgency model missing critical urgent emails | Sprint 3 | ML Team | Logical | Added rule-based urgency keyword overrides | 2025-12-30 | Closed | Critical emails detected
9 | QA team | 2025-12-31 | False positives in high-urgency predictions | Sprint 3 | ML Team | Logical | Refined urgency keyword list | 2026-01-01 | Closed | Precision improved
10 | QA team | 2026-01-02 | Conflict between ML urgency score and rule-based score | Sprint 3 | Backend Team | Logical | Implemented hybrid scoring logic | 2026-01-03 | Closed | Hybrid logic validated
11 | QA team | 2026-01-04 | High latency in urgency scoring service | Sprint 3 | Backend Team | Maintainability | Implemented asynchronous processing and caching | 2026-01-05 | Closed | Latency reduced
12 | QA team | 2026-01-10 | Dashboard not updating after backend API changes | Sprint 4 | Frontend Team | Maintainability | Re-linked dashboard with updated API routes | 2026-01-13 | Closed | Issue resolved
13 | QA team | 2026-01-12 | Category and urgency filters not working correctly | Sprint 4 | Frontend Team | User Interface | Fixed filter logic and state handling | 2026-01-15 | Closed | Filters functioning
14 | QA team | 2026-01-17 | Minor UI alignment and label inconsistencies | Sprint 4 | Frontend Team | User Interface | Adjusted CSS layout and corrected labels | 2026-01-22 | Closed | Presentation-ready

## Sheet2
Logical
User Interface
Maintainability
Standards
Others